PDO TEMPORAL DRIFT

CHARACTERIZATION PROJECT

Genomic, Transcriptomic & Functional Drift of Patient-Derived Organoids Over Time

| Project Title | PDO Temporal Drift Characterization Study |
| --- | --- |
| Project Code | PDO-DRIFT-001 |
| Version | 1.0 — Initial Research Protocol |
| Classification | Multi-Omic Longitudinal Study |
| Primary Aims | Passage Evolution · Growth Kinetics · Freeze-Thaw Impact |
| Study Duration | 18 months (Phases I–IV) |
| Target PDO Lines | 10–15 patient-derived organoid lines (mixed tumor types) |
| Document Date | March 5, 2026 |

# Executive Summary

Patient-derived organoids (PDOs) are three-dimensional, self-organizing tissue cultures that closely recapitulate the architecture, molecular identity, and drug-response profiles of their tumor or tissue-of-origin. They have emerged as powerful pre-clinical models for oncology drug discovery, biomarker validation, and personalized medicine. However, like all cell-based models, PDOs are susceptible to culture-induced changes — collectively termed "temporal drift" — that may silently erode their fidelity to the source tissue over time.

This project addresses a critical, undercharacterized threat to PDO-based research: systematic, time-dependent divergence at the genomic, transcriptomic, and functional levels. Drift may arise from clonal selection pressure, culture adaptation, epigenetic remodeling, stochastic mutation accumulation, or batch effects introduced by cryopreservation cycles. If left undetected, drift can generate irreproducible results, invalidate biomarker discovery efforts, and undermine the translational relevance of PDO-based drug screening.

Three Core Research Questions This Project Will Answer: - How do PDO lines evolve genetically and transcriptionally across serial passages (P2–P20+)? - Why do certain PDO lines proliferate faster, and what molecular programs underpin differential growth kinetics? - Does freeze-thaw cycling introduce quantifiable molecular or functional perturbations that persist beyond initial recovery?

The project integrates whole-exome sequencing (WES), RNA-sequencing (RNA-seq), reduced-representation bisulfite sequencing (RRBS), high-content imaging, viability assays, and multi-drug pharmacological profiling into a unified, time-resolved analytical framework. All data will be deposited into a curated PDO biobank registry with passage-resolved molecular fingerprints, enabling retroactive QC and cross-study comparisons.

# 1. Scientific Background & Rationale

## 1.1  PDOs as Pre-clinical Models

PDOs are derived from primary patient biopsies, surgical resections, or circulating tumor cells. When embedded in extracellular matrix (e.g., Matrigel or BME) and cultured in defined growth factor media, they self-organize into three-dimensional structures that preserve histological architecture, molecular heterogeneity, and importantly, drug sensitivity profiles that correlate with in vivo patient outcomes.

Published studies across colorectal, pancreatic, breast, lung, and prostate cancers have demonstrated that PDO pharmacological responses mirror patient responses with positive predictive values of 70–90%. This has catalyzed widespread adoption of PDOs in co-clinical trials, precision oncology pipelines, and large-scale compound screening platforms.

## 1.2  The Problem of Temporal Drift

Despite their promise, PDOs are living cultures subject to the evolutionary pressures inherent in any proliferating cell population. Unlike isogenic cell lines, PDOs begin as complex, heterogeneous mixtures of cells. Over time, subclones with proliferative advantages selectively dominate the culture — a process entirely analogous to Darwinian selection operating at the culture level.

| Known Sources of Genomic Drift - Clonal selection of fast-growing subpopulations - De novo somatic mutations from replication errors - Copy number alterations under in vitro pressure - Loss of heterozygosity at tumor suppressor loci - Chromosomal instability events (CIN) - Culture medium adaptation driving selection | Known Sources of Transcriptomic Drift - Epigenetic remodeling (promoter methylation shifts) - Loss of stromal/immune signaling inputs in vitro - Culture medium composition driving transcriptional state - Hypoxia-induced transcriptional reprogramming - EMT-like transitions under prolonged culture - Non-cell-autonomous signaling disruption |
| --- | --- |

## 1.3  Gap in Current Knowledge

While temporal drift is widely acknowledged as a concern among practitioners, the field lacks: (1) systematic, multi-omic characterization across a broad panel of PDO lines with matched clinical metadata; (2) defined passage thresholds beyond which drift becomes functionally significant; (3) standardized assay panels that can detect drift early; and (4) an understanding of how cryopreservation, a near-universal practice, contributes to molecular variation independent of passage number.

This project fills these gaps by implementing a comprehensive, longitudinal monitoring framework grounded in rigorous multi-omic profiling.

# 2. Specific Aims

Aim 1 — Genomic & Epigenomic Drift Across Serial Passages - Characterize somatic mutation trajectories, CNV evolution, and allele frequency shifts via WES at P2, P5, P10, P15, and P20 - Profile DNA methylation dynamics at key regulatory loci using RRBS at matched passage timepoints - Identify genomic events that correlate with functional phenotype change (growth, drug sensitivity) - Define passage thresholds at which genomic divergence exceeds 10% variant allele frequency shift

Aim 2 — Transcriptomic Drift & Differential Growth Kinetics - Perform bulk RNA-seq at P2, P5, P10, P15, and P20 for all PDO lines; apply single-cell RNA-seq at P5 and P15 for a subset of 5 lines - Identify transcriptional programs associated with fast vs. slow growth phenotypes using differential expression and GSEA - Map longitudinal changes in pathway activity (Wnt, MAPK, PI3K, EMT, cell cycle) across passages - Correlate transcriptomic drift magnitude with tumor-of-origin, genomic complexity, and culture conditions

Aim 3 — Molecular & Functional Impact of Freeze-Thaw Cycling - Systematically compare freshly passaged PDOs vs. post-thaw counterparts at matched passage using WES, RNA-seq, and functional assays - Quantify viability, proliferation kinetics, morphological parameters, and drug sensitivity pre- vs. post-cryopreservation - Identify transcriptional stress responses induced by freeze-thaw and determine their resolution kinetics - Develop standardized recovery windows (24h, 48h, 72h, 7d) after thaw before functional assays may be conducted

# 3. Experimental Design & Methods

## 3.1  PDO Line Selection & Establishment

A panel of 10–15 PDO lines will be selected to maximize diversity across tumor type, genomic complexity, and growth rate. Target enrollment includes at least 3 lines per cancer type from colorectal, pancreatic, and non-small-cell lung carcinoma, plus additional lines from breast and gastric cancer.

| Tumor Type | Target Lines | Growth Phenotype Mix | Tissue Source |
| --- | --- | --- | --- |
| Colorectal Carcinoma (CRC) | 3–4 lines | Fast + Slow | Surgical resection / biopsy |
| Pancreatic Ductal Adenocarcinoma | 3 lines | Slow + Moderate | EUS-FNA / surgical |
| Non-Small Cell Lung Cancer | 3 lines | Mixed | Bronchoscopy / resection |
| Breast Carcinoma | 2 lines | Fast + Slow | Core needle biopsy |
| Gastric Carcinoma | 2 lines | Mixed | Endoscopic biopsy |

## 3.2  Passage Regimen & Sample Collection

All PDO lines will be maintained under standardized, media-defined conditions specific to tumor type (e.g., IntestiCult, PancreaCult, PneumaCult) with weekly passaging. Samples for molecular assays will be harvested at predetermined passage numbers:

- Baseline (P2) — Early-passage reference; genomically closest to primary tumor

- P5, P10, P15, P20 — Serial passage timepoints; each harvested in triplicate

- Cryopreservation events at P5 and P10 — Freeze-thaw comparison at two biologically distinct passage stages

- Post-thaw recovery at 24h, 48h, 72h, and 7 days — Time-course for freeze-thaw functional recovery assessment

At each timepoint, samples will be split into: (1) molecular profiling aliquots (snap-frozen in liquid N₂), (2) functional assay aliquots (live culture), and (3) biobank cryovials (DMSO-based cryopreservation). A minimum of 5×10⁶ cells per aliquot will be collected.

## 3.3  Genomic Profiling (Aim 1)

### 3.3.1  Whole-Exome Sequencing (WES)

- Library preparation — Agilent SureSelect Human All Exon v7 capture (51 Mb)

- Sequencing depth — 150× mean target coverage; minimum 100× at all timepoints

- Platform — Illumina NovaSeq X Plus (2×150 bp paired-end)

- Matched normal — Patient-derived peripheral blood mononuclear cells (PBMCs) as germline reference

- Variant calling — GATK4 MuTect2 somatic pipeline; ensemble variant calling with VarScan2 and Strelka2

- CNV analysis — GATK4 CNV calling + GISTIC2.0 for recurrent focal events; allelic imbalance via FACETS

- Clonal architecture — PyClone-VI for cancer cell fraction estimation and clonal evolution tracking

### 3.3.2  Reduced-Representation Bisulfite Sequencing (RRBS)

- Coverage — ~4–5 million CpGs at >10× per site

- Analysis — Bismark alignment; MethylKit for differential methylation; GREAT for genomic annotation

- Focus regions — Promoters, CpG islands, enhancers, repetitive element methylation

## 3.4  Transcriptomic Profiling (Aim 2)

### 3.4.1  Bulk RNA-Sequencing

- Library — Poly-A selected; TruSeq Stranded mRNA kit; ≥30M reads per sample

- Alignment — STAR v2.7 + RSEM for quantification; DESeq2 for differential expression

- Pathway analysis — GSEA with MSigDB Hallmark + C2/C6 collections; Gene Ontology enrichment

- Splicing — rMATS for alternative splicing events; potential neoantigenic splice variants

- Fusion transcripts — STAR-Fusion; validation by RT-PCR for high-confidence calls

### 3.4.2  Single-Cell RNA-Sequencing (scRNA-seq)

Applied to 5 selected lines at P5 and P15 to characterize intra-culture heterogeneity and identify rare subpopulations driving drift.

- Platform — 10x Genomics Chromium v3.1; target 8,000–10,000 cells per sample

- Analysis — Seurat v5 pipeline: QC, normalization, dimensionality reduction (UMAP), clustering

- Trajectory — Monocle3 pseudotime analysis for lineage inference

- Integration — Harmony for batch correction across timepoints; CellChat for cell-cell communication

## 3.5  Functional Drift Assessment (Aim 3)

### 3.5.1  Proliferation & Growth Kinetics

- 3D growth curves — CellTiter-Glo 3D at 24h, 48h, 72h, 96h, 120h after re-seeding (n=6 replicates)

- Organoid size quantification — High-content imaging (Operetta CLS or ImageXpress Confocal); CellProfiler pipeline for area, volume, circularity

- Doubling time calculation — Non-linear regression; Gompertz growth model fit for each line × passage × condition

- Live/dead discrimination — Calcein-AM / EthD-1 staining; automated image analysis

### 3.5.2  Drug Sensitivity Profiling

A standardized 48-compound pharmacological panel will be tested at all passage timepoints and post-freeze conditions to detect functional drift:

- Panel composition — 15 standard-of-care agents + 15 targeted agents (EGFR, BRAF, MEK, PI3K, CDK4/6) + 8 epigenetic compounds + 10 emerging agents

- Dose-response — 8-point concentration curves; 10 nM–100 μM range; 72h exposure

- Readout — CellTiter-Glo 3D; IC50, AUC, Emax derived per compound

- Reproducibility threshold — IC50 shift >3-fold considered functionally significant drift

### 3.5.3  Morphological Phenotyping

- Brightfield morphology — Automated Nikon Ti2 widefield; structured morphology scoring rubric

- Immunofluorescence panel — Ki67 (proliferation), Cleaved caspase-3 (apoptosis), E-cadherin (epithelial), Vimentin (mesenchymal), EpCAM (stemness proxy)

- 3D confocal imaging — Leica SP8 or Zeiss LSM980; z-stack at P5, P10, P15 for selected lines

# 4. Integrated Analytical Framework

## 4.1  Multi-Omic Drift Score (MODS)

A central deliverable of this project is the development of the Multi-Omic Drift Score (MODS) — a composite, quantitative metric that integrates genomic, transcriptomic, and functional distance from the P2 baseline for each PDO line. This score will enable standardized comparison of drift magnitude across lines and conditions.

MODS Components & Weighting (Proposed): - Genomic distance (GD): cosine distance of somatic mutation burden + CNV profile from P2 baseline [Weight: 30%] - Transcriptomic distance (TD): Pearson correlation loss in global gene expression vs. P2, adjusted for batch [Weight: 35%] - Epigenomic distance (ED): CpG methylation beta-value deviation at differentially methylated regions [Weight: 15%] - Functional distance (FD): Drug sensitivity AUC shift score across 48-compound panel vs. P2 [Weight: 20%] - MODS = 0.30×GD + 0.35×TD + 0.15×ED + 0.20×FD (range: 0–1; threshold for flagging: MODS > 0.25)

## 4.2  Growth Kinetics Modeling

Differential growth kinetics between lines will be investigated using a multi-level analytical strategy:

- Transcriptional signature analysis — Identification of gene sets predictive of fast vs. slow growth using regularized regression (LASSO) on RNA-seq data

- Cell cycle profiling — FUCCI reporter system (if lentiviral transduction is feasible) or EdU incorporation for S-phase fraction quantification

- Metabolic profiling — Seahorse XFe96 for oxygen consumption rate (OCR) and extracellular acidification rate (ECAR); fast growers hypothesized to show Warburg shift

- mTOR/Wnt pathway activity — Phospho-proteomics (10-plex TMT) at P5 and P15 for 5 fast + 5 slow growth lines

## 4.3  Freeze-Thaw Analysis Pipeline

For each freeze-thaw comparison, a paired analysis will be performed contrasting the fresh (never-frozen) counterpart at matched passage with the post-thaw sample. The analysis will assess:

- Immediate transcriptional stress response — ER stress (ATF4, CHOP, XBP1s), heat shock proteins, apoptotic pathway activation

- Recovery trajectory modeling — Time-series RNA-seq at 24h, 48h, 72h, 7d post-thaw; convergence to pre-freeze state modeled as exponential decay

- Epigenetic persistence — RRBS comparison pre- vs. post-freeze; identify sites where methylation does not recover

- Functional washout period determination — Identify minimum post-thaw recovery time at which drug sensitivity profiles are indistinguishable from fresh counterparts

# 5. Project Phases, Timeline & Deliverables

| Phase | Duration | Focus | Key Deliverable |
| --- | --- | --- | --- |
| Phase I | Months 1–3 | PDO biobanking, line selection, baseline profiling (P2), protocol standardization | Baseline multi-omic dataset; QC-passed PDO registry |
| Phase II | Months 4–9 | Serial passage profiling (P5–P15), growth kinetics experiments, freeze-thaw experiments for P5 cohort | Passage-resolved WES + RNA-seq + functional dataset |
| Phase III | Months 10–14 | Extended passage profiling (P20), scRNA-seq runs, metabolomics + phospho-proteomics, freeze-thaw P10 cohort | MODS score development; single-cell atlas; freeze-thaw recovery model |
| Phase IV | Months 15–18 | Integrated data analysis, MODS validation, manuscript preparation, biobank finalization | MODS framework; PDO drift guidelines; peer-reviewed publications |

## 5.1  Key Deliverables

| Aim | Assay / Method | Timepoints | Output Metric |
| --- | --- | --- | --- |
| Aim 1 | WES (all lines × 5 timepoints) | P2/P5/P10/P15/P20 | Somatic VAF trajectories, CNV evolution maps, clonal evolution trees |
| Aim 1 | RRBS methylation profiling | P2/P10/P20 + post-thaw | Differential methylation regions (DMRs), CpG drift index |
| Aim 2 | Bulk RNA-seq | P2/P5/P10/P15/P20 | Transcriptional drift score, pathway activity vectors |
| Aim 2 | scRNA-seq (5 lines) | P5 and P15 | Cell population composition shift, trajectory pseudotime maps |
| Aim 2 | Growth kinetics assay | Weekly (all passages) | Doubling time table, growth-predictive gene signature |
| Aim 3 | Drug sensitivity panel (48 agents) | All passages + post-thaw | IC50/AUC matrices, functional drift score per compound |
| Aim 3 | Post-thaw RNA-seq time series | 24h/48h/72h/7d | Transcriptional recovery half-life, persistent perturbation loci |
| All | Multi-Omic Drift Score (MODS) | Per passage & condition | Composite drift score for each line; flagging thresholds |

# 6. Bioinformatics Infrastructure & Data Management

## 6.1  Computational Pipeline Architecture

All analyses will be executed via containerized, reproducible workflows using Snakemake or Nextflow pipeline management systems. Compute infrastructure will leverage HPC cluster allocation (SLURM scheduler) with dedicated GPU nodes for deep learning-based image analysis modules.

- Version control — All pipeline code on GitHub (private repository); tagged releases per project phase

- Containerization — Docker + Singularity images for all analysis environments; pinned dependency versions

- Data storage — Tier-1 NAS (raw FASTQ + BAM: ~50 TB projected); Tier-2 cloud archive (AWS S3 Glacier)

- Metadata management — ISA-Tab compliant metadata schema; integration with BioSample/dbGaP for eventual public deposition

- Interactive visualization — R Shiny application for real-time MODS tracking and per-line QC dashboards

## 6.2  Statistical Framework

All primary statistical analyses will be pre-registered via OSF (Open Science Framework) prior to data collection to minimize post-hoc analytical bias. Key statistical considerations include:

- Multiple testing correction — Benjamini-Hochberg FDR for gene-level tests; Bonferroni for primary endpoints

- Mixed-effects modeling — Linear mixed models for longitudinal transcriptomic data (passage as time variable; line as random effect)

- Power analysis — Minimum 80% power to detect 2-fold expression change at FDR <5% with n=3 biological replicates per timepoint per line

- Dimensionality reduction — PCA, UMAP, and t-SNE for exploratory analysis; MOFA+ for multi-omic factor analysis

# 7. Expected Outcomes & Significance

## 7.1  Scientific Contributions

This project will generate the most comprehensive, multi-omic, longitudinal characterization of PDO temporal drift assembled to date. The primary scientific contributions are anticipated to include:

- A passage-resolved, multi-omic atlas of genomic and transcriptomic drift across 10–15 PDO lines representing 5 major cancer types — a publicly accessible resource for the organoid research community.

- Definition of critical drift thresholds — specific passage numbers and MODS values beyond which PDO molecular profiles diverge significantly from the source tumor, providing practical guidance for researchers.

- Identification of molecular mechanisms underlying differential growth kinetics — new biological insights into why certain PDO lines outcompete others, with potential implications for clonal evolution theory.

- Characterization of freeze-thaw-induced molecular perturbations and recovery kinetics — enabling evidence-based recommendations for minimum post-thaw recovery periods before conducting functional assays.

- Validation and public release of the Multi-Omic Drift Score (MODS) framework — a standardized tool for PDO quality assessment applicable across laboratories worldwide.

## 7.2  Translational Impact

Beyond basic science, this project addresses tangible translational bottlenecks:

- Drug discovery — Establishes confidence limits for PDO-based drug screening data based on passage-quality certification

- Biomarker development — Ensures PDO-derived biomarker signatures are not artifacts of culture-induced drift

- Co-clinical trial design — Informs PDO banking protocols for prospective clinical studies, minimizing inter-site variability

- Regulatory science — Provides data to support FDA and EMA guidance on PDO model qualification for IND-enabling studies

## 7.3  Anticipated Publications

- Manuscript 1 (Month 14) — Primary research article: Multi-omic characterization of genomic and transcriptomic drift in PDOs across serial passage — Nature Methods or Cell Systems

- Manuscript 2 (Month 15) — Research article: Molecular determinants of differential growth kinetics in PDOs — Cancer Research or Oncogene

- Manuscript 3 (Month 17) — Methods article: MODS — a composite drift scoring framework for PDO quality control — eLife or PLOS Biology

- Data descriptor (Month 18) — PDO Temporal Drift Atlas: A multi-omic, passage-resolved resource — Scientific Data

# 8. Quality Control & Risk Mitigation

## 8.1  PDO Culture QC Thresholds

Each passage event and sample collection will be gated on the following minimum quality criteria before proceeding to molecular profiling:

| QC Parameter | Minimum Threshold | Remediation if Failed |
| --- | --- | --- |
| Cell viability (trypan blue) | ≥85% viable at harvest | Repeat passage; investigate media lot |
| Mycoplasma status | Negative (monthly testing) | Discard line; restore from biobank |
| STR profiling (6-monthly) | ≥80% concordance with P2 reference | Flag line; increase WES priority |
| Organoid morphology score | ≥3/5 structured morphology | Document; include as covariate |
| RNA integrity (RIN) | ≥7.0 for RNA-seq libraries | Re-extract; adjust homogenization |
| WES target coverage | ≥100× at 90% of target bases | Re-sequence affected sample |

## 8.2  Risk Register

High-Priority Risks & Mitigations: - Risk: PDO line contamination or loss — Mitigation: Biobank cryovials at every 5th passage (minimum 5 vials); monthly mycoplasma testing; STR authentication every 6 months - Risk: Inter-operator technical variability inflating biological drift signal — Mitigation: Written SOPs for all culture steps; operator-blinded randomization of passage order; inclusion of technical replicates - Risk: Insufficient cell yield for multi-omic profiling at later passages — Mitigation: Low-input library protocols (Smart-seq3, SRSLY); scale-up culture vessels at P15+ - Risk: Loss of clinical annotation integrity — Mitigation: REDCap database with audit trail; double data entry for all clinical metadata; de-identification pipeline - Risk: Computational resource bottlenecks — Mitigation: Pre-allocated HPC core-hours; cloud burst capacity via AWS on demand

# 9. Team, Roles & Resource Requirements

## 9.1  Proposed Team Structure

| Role | Effort (FTE) | Responsibilities |
| --- | --- | --- |
| Principal Investigator | 0.20 FTE | Scientific leadership, grant oversight, manuscript senior authorship |
| Co-Investigator (Bioinformatics) | 0.30 FTE | Pipeline development, MODS framework, data management, computational analysis |
| Research Scientist (PDO Biology) | 1.00 FTE | PDO culture, passaging, cryopreservation, functional assays |
| Postdoctoral Fellow (Genomics) | 1.00 FTE | WES/RRBS library prep, genomic analysis, clonal evolution modeling |
| Postdoctoral Fellow (Transcriptomics) | 1.00 FTE | RNA-seq/scRNA-seq, transcriptional drift analysis, manuscript preparation |
| Research Technician | 1.00 FTE | Cell culture support, QC assays, biobanking, administrative lab tasks |
| Biostatistician (part-time) | 0.20 FTE | Study design, power calculations, primary endpoint statistical analysis |

## 9.2  Estimated Budget Summary

| Budget Category | Per Year (Est.) | 18-Month Total |
| --- | --- | --- |
| Personnel (5.5 FTE total) | $520,000 | $780,000 |
| Sequencing (WES, RNA-seq, RRBS, scRNA-seq) | $180,000 | $270,000 |
| Cell culture consumables & reagents | $60,000 | $90,000 |
| Functional assay reagents & drug compounds | $30,000 | $45,000 |
| Proteomics / metabolomics (outsourced core) | $40,000 | $60,000 |
| High-content imaging consumables | $15,000 | $22,500 |
| Computational resources (HPC + cloud) | $20,000 | $30,000 |
| Indirect costs (estimated @ 55%) | $473,500 | $710,250 |
| TOTAL ESTIMATED BUDGET | $1,338,500 | $2,007,750 |

# 10. Ethical, Regulatory & Data Governance Considerations

## 10.1  Human Subjects & Tissue Procurement

All PDO lines will be derived from patient tissue collected under IRB-approved biobanking protocols. Informed consent will include explicit language permitting organoid derivation, extended in vitro culture, genomic profiling, and sharing of de-identified molecular data in public repositories. Patients will retain the right to withdraw consent for future data use.

- IRB protocol — Existing institutional biobank protocol (amendment required for passage-extended profiling)

- Data de-identification — HIPAA Safe Harbor standard; all samples assigned anonymous PDO-IDs

- Incidental findings policy — Genomic findings with clinical significance to be referred per institutional return-of-results SOP

## 10.2  Data Sharing & Open Science

- Raw sequencing data — dbGaP deposit upon first publication (controlled access for human genomic data)

- Processed data & MODS scores — GEO deposit for transcriptomic data; SRA for raw reads; GitHub for code

- PDO biobank resource — Lines available to qualified academic researchers through MTA after publication

- Pre-registration — OSF pre-registration of primary hypotheses and statistical analysis plans prior to data collection

PDO Temporal Drift Characterization Project  |  Protocol Version 1.0

This document is confidential and intended for internal research planning purposes only.